## Sprint-1
Sprint Planning
Sprint # | Sprint:1
Sprint Name | Wireframe & Documentation
Sprint Goal | To build a base for Open M4S, Complete Documentation
Team Member | 8 | Anwar,Qasim,Zia,Nahyan,Saleem,Zahid,Yahya,Iftihar
Sprint Start Date | 2014-03-03
Sprint Duration | 12 | Days
End Date | 17/03/2014
Story Name | Tasks Description |  | Assigned To | Start Date | End Date | Status
MCS Documentation | Document Format, Workflows,Techologies,Functionality |  | Saleem | 2014-03-03 | 17/03/2014 | Done
Open M4S Wireframe | Wire frame for all modules,Dasboard,login and Settings |  | Zia | 2014-03-03 | 17/03/2014 | Done
GeoNetwork Study | Study ,Installation,Knowledge Sharing |  | Nahyan | 2014-03-03 | 17/03/2014 | Done
Open Geo | Study ,Installation,Knowledge Sharing |  | Zia | 2014-03-03 | 17/03/2014 | Done
Mapping,GIS | Study,Example, Knowledge Sharing |  | Iftihar | 2014-03-03 | 17/03/2014 | Done
Sola | Study ,Installation,Knowledge Sharing |  | Saleem | 2014-03-03 | 17/03/2014 | Done
SOA | Study ,Installation,Knowledge Sharing |  | Yaya | 2014-03-03 | 17/03/2014 | In Progress
Wireframe(4 Modules) | Wire frame and documention |  | Qasim | 2014-03-03 | 17/03/2014 | Done
ERP Documentation | Study ,Installation,Knowledge Sharing |  | Zahid | 2014-03-03 | 17/03/2014 | In Progress

## Sprint-2
Sprint Planning
Sprint # | Sprint:2
Sprint Name | Prototype
Sprint Goal | Prototype for Open M4S
Team Member | 5 | Zia,Nahyan,Saleem,Zahid,Yahya,Iftihar
Sprint Start Date | 18/3/2014
Sprint Duration | 10 | Days
End Date | 31/03/2014
Story Name | Tasks Description |  | Assigned To | Start Date | End Date | Status
Dashboard | Customization,View,Dashoard in Bootstrip |  | Nahyan | 18/3/2014 | 31/03/2014 | In Progress
Database | Specail Database Study,PostGIS, PostGres SQL,ERD |  | Zia | 18/3/2014 | 31/03/2014 | In Progress
Webservice,API | Webservise, API,XML Write/Read |  | Saleem | 18/3/2014 | 31/03/2014 | In Progress
Mapping,GIS | Base knowelge About GIS, 3D Modeling Examples |  | Iftihar | 18/3/2014 | 31/03/2014 | In Progress
SOA | Study ,Installation,Workflows |  | Yaya | 18/3/2014 | 31/03/2014 | In Progress
ERP Documentation | Study ,Installation,Knowledge Sharing |  | Zahid | 18/3/2014 | 31/03/2014 | In Progress

## Sprint-3
Sprint Planning
Sprint # | Sprint:3
Sprint Name | Mineral Cadaster System(MCS) Sartup
Sprint Goal | Start work on Mineral Cadaster System(MCS)
Team Member | 5 | Zia,Nahyan,Saleem,Zahid,Yahya,Iftihar
Sprint Start Date | 2014-01-04 |  |  | Nahyan | Saleem | Zia
Sprint Duration | 15 | Days |  | Yahya | Iftihar | Bahar
End Date | 15/04/2014 |  |  | Zahid | Imdad
Story Name | Tasks Description |  | Assigned To | Start Date | End Date | Assign To
MCS View | View for MCS, Client Side Development |  | Nahyan | 2014-01-04 | 15/04/2014 | Nahyan
Webservice,API | MCS Based API for Get,Set and Retrieval |  | Saleem | 2014-01-04 | 15/04/2014 | Saleem
Database | MCS Database, GeoEXT |  | Zia | 2014-01-04 | 15/04/2014 | Zia
Mapping,GIS | Base knowelge About GIS, 3D Modeling Examples |  | Iftihar | 2014-01-04 | 15/04/2014 | Iftihar
SOA | Workflows and SOA Based Infrastucture, Documentation |  | Yaya | 2014-01-04 | 15/04/2014 | Yayha
ERP | Vehical Managemenst System for Mine Management |  | Zahid | 2014-01-04 | 15/04/2014 | Zahid
Task No# | Tasks Description |  | Assigned To | Start Date | End Date | Status
1 | View for Request list
2 | View Request Details
3 | Add new Request
4 | CreateRequest API
5 | Return list of Requests API
6 | Add new Request API
7 | Return Detail by Request ID API
8 | Applicant Request Table
9 | Coodinates Table
10 | Database Documents
11
12
13
14
15
16